### Understanding success and failure of anti-corruption initiatives

Richard Heeks, Director, Centre for Development Informatics, University of Manchester http://www.cdi.manchester.ac.uk/

Harald Mathisen, Senior Programme Coordinator, U4 Anti-Corruption Resource Centre, Chr. Michelsen Institute, http://www.u4.no

#### Abstract

This paper focuses on the success and failure of anti-corruption initiatives; focusing mainly on those in developing countries.  Through a review of extant evidence, it finds a very mixed picture within which there is widespread failure; albeit sometimes only partial failure.  As a result, anti-corruption as a field can struggle to gain attention and resources among competing development initiatives.

In reviewing that field we find that, while some progress has been made – for example in integrating risk assessments into programs and in learning from political economy analysis – there is little actual focus on the “missing middle”: the interventions themselves and how they can be made to work better. In analyzing those interventions, we argue that projects mostly fail because of over-large “design-reality gaps”; that is, too great a mismatch between the expectations built into their design as compared to on-the-ground realities in the context of their implementation. Successful initiatives find ways to minimize or close these gaps. Effective design and implementation processes enable gap closure and improve the likelihood of success.

Introduction

Most anti-corruption initiatives in developing countries fail. This article sets out to understand why that is, and what might be done about it. Our remedy does not consist of a generic design approach that if applied will create success; it is precisely this form of oversimplification and one-size-fits-all approach that lead interventions off track.

More needs to be done to map and understand the many reasons for failure of conventional anti-corruption initiatives. While corruption can exist in all countries and organizations and cannot be eliminated entirely, this article takes as its starting point that through successful reforms it can be reduced or minimized to a certain level.

This investigation is inspired by Pritchett et al. [22], who argue of international development interventions that “implementation remains conspicuously under-appreciated, under-theorized and under-researched”, and suggest a realignment of our focus from the theoretical to the practical, “intellectual heavy lifting in development is thought to center on defining objectives, promoting goals, designing policies and formulating strategies”. We want to take the focus back to the basics, to create solid interventions, one by one, and from that scale up success rather then failure. Our contribution is to suggest a move away from grand designs developed by technocrats to a focus on interventions that have local fit and strategic fit in direct support of the governance agenda.

This analysis is developed as follows. In the first sections we discuss the strategic considerations we make and the tools we use to encourage reform, and we report on the status of the fight against corruption globally. Our argument is that in the field of anti-corruption, some progress has been, for example in integrating risk assessments into programs and in learning from political economy analysis, but there is little actual focus on the “missing middle”, the interventions themselves and how they can be made to work better. In the second section we analyze those interventions, and argue that projects mostly fail because of over-large “design-reality gaps”; that is, too great a mismatch between the expectations built into their design as compared to on-the-ground realities in the context of their implementation. Successful initiatives find ways to minimize or close these gaps. Effective design and implementation processes enable gap closure and improve the likelihood of success.

In defense of governance

Having worked directly with development agencies and their staff for many years the authors see growing signs of doubt in the governance and anti-corruption agenda. It might seem overambitious, and too much is promised in terms of delivering aggregate public goods like economic growth and stable democratic systems. The relative lack of progress puts strain on practitioners and policy-makers alike and leads to soul searching and self-flogging so intense that the overall goals of sustainable development have become blurred. The interest in titles such as “an upside down view of governance” [16] indicates that the very premise of the current development paradigm on governance and anti-corruption is being challenged.

The governance reform agenda then, if not seen as an integral component of the reinvigorated focus on results, outcomes and impact that is sweeping across the field, might come to be substituted by reform initiatives where results are more easily measurable. Now if governance; “addresses the very institutional underpinnings of economic and political development” [10], and if one agrees that no country has advanced without a functional level of governance, then great efforts should be made to counter such a trend.

In charting a way forward we are not taking the traditional approach of suggesting the introduction of new development actors, a greater focus on international aspects of corruption, or that attending to the demand side of governance reforms will solve most problems. Nor do we blame lack of political will or capacity constraints. The starting point is simple; anti-corruption is competitive: if successful it will create losers, and the corrupt tend to fight back. But reform will also create winners and opportunities for rent-seeking; most notably per diem practices and other small frauds, and multiple opportunities related to contracting of technical assistance projects. What is needed therefore is a strategic approach; one that creates success from the ground up, and scales up based on results that all stakeholders can relate to, thus promoting sustainable interventions.

The challenge then is to find out how we can get a more meaningful return on the heavy investments made into governance reform.

The fight against corruption – a status report

What can we say about the status of anti-corruption initiatives? In some ways, it seems, relatively little, as far too few resources are spent on learning from interventions, and little is understood about the factors that make them happen. Very few careful reviews and evaluations are available, and seldom does their focus go beyond one locality, thus precluding wide-ranging conclusions. That said, the aim is not to create a catalogue of intervention that we can superimpose onto any country or reform process – one size does not fit all.

Even the most basic M&E practices are not adhered to; such as collecting meaningful baseline data that would enable us to track progress over time. As a result there is a tendency to measure processes in the form of the functional effectiveness of the initiatives themselves, and never their impact on governance overall. Moving to check for intended results is obviously more costly and complicated,  but as it stands the suspicion is that such an exercise is avoided as it may document outright failure [21].

Another set of arguments may stand in defense of current interventions, i.e. a recognition that reform processes may take decades to take hold, as they are chipping away at the margins of a major societal problem – hence calls for timelines and expectations to be adjusted so that capacities can be built and transformed.

The limited research that has been carried out has a typical chronology: initial claims of success for initiatives are later scaled-back to tell a less positive story. From the early optimism of the Independent Hong Kong Anti Corruption Commission a number of shortcomings are now evident with the formal oversight institutions. While Anti-Corruption Agencies are the most prominent area for support, they have, “with one or two exceptions, been a disappointment” [31]. The same pattern emerges from an overview of the literature on Rule of Law-based initiatives: they are quite simply lamented [25].

Claims about the support for anti-corruption offered by civil society and the media should also be handled with caution. In the 1990s, such support was seen as an essential means to boost demand for good governance. But latterly, this type of support is itself seen to often face serious integrity challenges [28]. Its impact is now more contested and some research warns us that such a focus can backfire, especially where state capacities and legitimacy are contested [27]. Some claim that attempts to create demand for good governance from below have fared better, i.e. when people are given the tools to provide oversight over the processes that affect their livelihoods.  For example, Reinikka and Svensson [23] report the positive experience of doing public expenditure tracking surveys and providing access to information in Uganda. Yet here, too, there are concerns, with others reporting that the progress was made due to better control and management from the center [14], or that results are not so positive in other contexts [26]. McGee & Gaventa’s [18] very comprehensive review of the impact and effectiveness of accountability projects gives a mixed picture, where evidence on impact is uneven, and “still remarkably sparse”.

Within the governance field most resources are used to improve the key functions of the state: effective public sector management and public financial management. While faring better than most other reform areas, such nationwide reforms are often embedded in large national anti-corruption plans which are weakly coordinated, have no matching resource base, and lack credible implementation strategies. Often progress slides back and overall most analysts conclude that anti-corruption policies in most countries “have not been overly successful” [15]. The World Bank IEG’s evaluation notes: “Indirect measures to reduce public sector corruption, such as simplifying procedures and regulations, moving to e-government, and rationalizing and improving human resources management, were more successful. Even in these latter areas, however, there were weaknesses related to lack of diagnostic tools, poor tailoring of proposals to the specific situation on the ground, and therefore a lack of realism in terms of sequencing, speed and comprehensiveness of reform proposals: they tended to be too ambitious and thus exceeded the governments’ capacities to implement.” [34].

At the aggregated level a recent analysis funded by key aid providers on the impact of their interventions, covering five countries, reports mixed success and questions whether donor efforts have made a positive overall impact in reducing corruption. The report goes on to speculate on the degree to which donors have fuelled rather the reduced corruption given the large sums of money being poured into sector work [17]. In line with these findings Mutebi [19] concludes “there is mounting evidence that anti-corruption policies and mechanisms … often fail, and at times fail miserably.” In Africa international anti-corruption efforts, are deemed to be “a failure” [7]. For other regions the Control of Corruption Indicator, which is included in the World Bank global survey of governance, shows that the same pattern is true for most regions. A time series from 1996-2010, shows overall stagnation, and puts Sub-Saharan Africa at the bottom, which underlines the failure given that most resources have been invested in this region.

Bad news travels fast but some sporadic success stories do exist, mostly in working with specific sectors, e.g. health and business, education, and financial management [30]. And in defense of current anti-corruption interventions progress has been made in the following ways:

- Awareness and knowledge has deepened, and diagnostic tools have improved, thus making conversations about corruption a taboo only in a handful of cases.

- International and national legal frameworks (conventions) have been improved.

- International and transnational aspects of corruption such as illicit capital flight and money laundering are more in the limelight.

- Promising long-term reforms of public institutions are underway in a great number of countries.

- An understanding has developed that the demand side of reforms in general and in civil society in particular can play a vital role if linked to supply side interventions.

- There is greater recognition of the importance of collaborations and partnerships (Paris & Accra).

Overall, then, we can say that there is a mixed picture, but with widespread (though sometimes only partial) failure. Unfortunately, these past anecdotes of success and failure seem contradictory, and the many contested notions lead to endless and indeed fruitless discussions and take our focus away from learning how to create successful interventions. A first step will be diagnosis – understanding some of the key causes of implementation problems.

We have a problem - do we have an agreed way forward?

Within rather limited and mixed evidence, then, we see a fairly consistent pattern of shortcomings in anti-corruption initiatives. This perceived weakness is causing great difficulties for those who work on anti-corruption within development agencies. They have to justify the resources used for “soft” interventions and compete for funds with high-profile campaigns that promote hardware like bed nets and vaccines, or advocate revolutionary solutions like property rights for all. The donor community’s preoccupation with results and reporting thus reinforces the competitive disadvantage of anti-corruption work. Not being able to show short-term impact of interventions is likely to make the advocates for long-term governance reform expendable.

Anti-corruption is also highly controversial among those who offer support in this area, with tensions arising between the prevention and enforcement communities. The lack of measurable results from preventive-type activities has pushed the enforcement community into the limelight. They are being given more resources and media coverage, and have been encouraged to develop alternative strategies that more aggressively pursue a global enforcement agenda focused on issues like illicit capital flight, asset forfeiture and recovery – all expected by the World Bank [33] to “yield higher-end results”.

We welcome these new additions to the toolbox in the fight against corruption, but want to reform the way in which the more traditional measures of technical assistance, capacity building and demand-side interventions for governance can be made to work better. The lack of results achieved thus far should spur better engagement, not less.

As development interventions of all types fail with some regularity, why then expect more from governance and anti-corruption interventions? The reasons for these persistent failures are multifaceted, but basic political economics holds the most salient overall explanation: few if anyone in a position of power and benefiting from corruption would like to see the opportunities for extraction reduced. For them reform and plunder are antithetical [24].

Good execution means better understanding of key context-specific factors that affect implementation. These include: the degree to which corruption practices are accepted at the local level; how petty corruption is a part of grand systemic corruption networks; the interplay of formal and informal institutions; etc.

One example of not understanding local power structures well comes from an insightful study of the efforts to curb corruption in the Uganda Revenue Authority (URA), Fjeldstad [9] argues that the technocratic remedies supported by donors have underplayed the degree to which progress in tax administration depends upon a thorough ‘cultural change’ in the public service. Fjeldstad shows that the motives of individual actors are often inextricably tied to the interests of the social groups to which they belong. In the URA, he argues, patronage runs through networks grounded on ties of kinship and community origin. As such, people recognize the benefits of large extended families and strong kinship ties, even as their social and economic aspirations may be indisputably modern. This implies that such social relations may undermine formal bureaucratic structures and positions. If these problems, which are rooted in social norms and patterns of behavior rather than in administrative features, are overlooked, the result may be to distort incentives. As a consequence, the government's commitment to reforming the tax administration may also be undermined. However, such local factors are often overlooked, and there is still a tendency for anti-corruption programs to be “one-size-fits-all”.

Not understanding local power structures and making prescription without proper diagnosis is exacerbated by the international development community being at odds with itself over which key strategic directions to take when proposing interventions, like whether:

- Corruption must be eradicated through in-depth reforms in all sectors <=> A selective approach that focuses on creating success through discrete interventions and building from the positive momentum created.

- High-level political will is an absolute precondition for success of an anti-corruption strategy or intervention <=> An analysis of the context, of competition, and of incentives for reform by key stakeholders, thus finding entry points at lower levels.

- Technical solutions working under the radar of corrupt government officials have a greater chance of succeeding <=> Corruption is a political problem and demands political solutions, hence a more confrontational strategy.

- The public must be sensitized and convinced that corruption is evil <=> A focus on building the legitimacy of the state and key institutions through making real changes in the daily lives of the population.

These tensions over key strategic choices have themselves been problematic, though, in directing attention away from the nitty-gritty of interventions. More generally, and for some of the reasons already identified, most discussions in development circles tend to regress to a common pattern: donors blame the government, governments blame donors, and non-state actors blame everyone excluding themselves!

Analysis of the critical aid literature, and several SWOT exercises conducted on anti-corruption initiatives during U4 Anti-Corruption Resource Centre training sessions also reflects this pattern.

Table 1: Reasons given for the failure of anti-corruption interventions.

| Mistakes typically attributed to donors | Mistakes typically attributed to governments | Mistakes shared between donors and governments | Mistakes attributed to the implementation itself |
| --- | --- | --- | --- |
| - Reforms reduced to technical changes in “governance”, based on principal-agent theory, politics of reform overlooked - Corruption perceived as a generic problem – recommendations vary little from one society to another - Approaches imposed from outside - Time frames for change are unrealistic: focus on immediate over meaningful reform - Incentives to change are not addressed - Overambitious - Lack of context sensitivity - Over funding and pressure to disburse - Reluctance to intervene in domestic [political] affairs - Weak accountability of donors to partners, - Over-reliance on NGOs - to the detriment of both state institutions and community involvement - Too little attention on the “supply side” – developed country firms | - Lack of political will - Lack of local ownership - Unrealistic, no resources attached - Plans being undifferentiated laundry list of reforms - Fragmentation and depletion of responsibilities - Failure to institutionalize reforms - Failure to deliver quick wins - Too dependent on law enforcement - Targeting only middle ranking officials | - Inadequate focus on outcomes - Defensiveness and lack of transparency - Poor supervision of projects - Poor coordination - Tendency to rely on external experts - Corruption and governance seen as a “sector” and not mainstreamed - Focus on just one reform area (like Anti-Corruption Agencies) | -Too few actors involved in interventions - Low level of long term partnership - No indicators for measuring outcomes and impact - Ill-conceived time frames |

The intensity of the debates and the very different perspectives reflected show more than anything the deep mutual distrust that lurks beneath pronouncements of partnership and mutual accountability. It shows how anti-corruption is clearly a competitive business; it creates winners and losers and is therefore highly political.

The other striking finding is the lack of attention paid to the anatomy of the interventions themselves: blame appears far more readily attached to stakeholders than to processes. The weak knowledge base has turned prescriptions into a weak list of principles for what not to do, or to a factor approach that provides a checklist of components or actions that should supposedly be included within all anti-corruption initiatives. The most often repeated recommendation is to avoid a one-size-fits-all approach (e.g. [5], [15], [32], [35]). But how can we find a way through this conundrum, taking robust and generic findings into account, yet simultaneously being sensitive to individual anti-corruption initiatives and to local circumstances?

The remainder of this article is devoted to the core issue that to date seems to have been ignored – the interventions themselves. As noted above, so much attention seems to have been devoted to the “top and tail” of corruption – to its causes and its effects – and/or has degenerated into a quasi-ideological set of arguments and “blame games”. What has disappeared from the spotlight – and which we wish to bring back – is the heart of anti-corruption: the practical mechanisms for fighting it [35]. It is to these and their role in implementation that we now turn.

#### The design-reality gap model

Beyond the rationales and reasons given above, the failure of anti-corruption initiatives is often seen as “by and large the result of an implementation problem” [20]. But part of the problem has often begun well before implementation; inscribed into the design of these initiatives. Anti-corruption reforms are part of a more general global diffusion – of knowledge and ideas, of skills and techniques, of technologies and tools – from perceived epicenters in the industrialized world to transitional and developing economies. So even though modernization theory – with its belief that development progresses by transferring a cookie-cutter set of institutional reform models from global North to global South – supposedly fell from favor four decades ago, we find its mentality still very much alive.

Such standardized transfers are problematic because – through their designs – they carry with them parts of the world from which they came. All anti-corruption designs contain within them an inscribed “world-in-miniature” which we may call requirements or assumptions or expectations about the context into which the initiative is going to be deployed. This includes inscriptions about the technology that will be available; about the values that people will have; about organizational culture; about work processes and structures; and so forth.

Of course, if these design expectations matched the realities of the deployment context, implementation would run smoothly. Unfortunately, this is rarely the case. Design expectations do not draw directly, or even predominantly, from the world of the actors who deploy and use the anti-corruption initiative, but from the world of the designer, which conditions the perceptions of the designer about the world of the user. Gaps therefore arise between the design expectations built into anti-corruption initiatives, and the reality of the context of deployment, as summarized in Figure 1.  We have already noted examples of this – in the IEG’s identification of “poor tailoring of proposals to the specific situation on the ground”, in the failure to understand local power structures in the case of the URA, and in the lack of realism noted in a number of issues raised in Table 1.

# Figure 1: Design-reality gaps in anti-corruption initiatives

In reviewing these and other initiatives and their outcomes we see that, the larger the gap between design and reality, the greater the risk of failure [11] [12]. This pattern is confirmed by an analysis of several capacity-building projects: “project recipients and other interested parties recognize immediately the difference between a project that has got to grips with what the problems really are and is genuinely trying to make a difference and one that completely misses the point, or is simply off-the-shelf, or going through the motions, or just fashion conscious” [3]. One key question is therefore; how can the nature of local fit – i.e. the gap between design vs. reality – be measured?

A variety of checklists could be used. Here we offer a checklist of seven ‘ITPOSMO’ dimensions, which have been developed and tested on a series of cases in developing countries, including anti-corruption initiatives, and found to cover the key features of such initiatives [12] [13]. They are: Information (both formal and informal), Technology (mainly information technology), Processes (from individual tasks to broader business processes), Objectives and values (covering formal strategies and personal goals, and the influence of informal institutional forces), Staffing and skills (the quantitative and qualitative aspects of competencies), Management systems and structures (the formal aspects of organization), and Other resources (especially time and money).

For each of the dimensions in turn, either an individual or a group of initiative stakeholders can analyze two things. First the reality relating to that dimension within the deployment context. Second, the assumptions and requirements relating to that dimension that are built into the initiative design. Any differences could be discussed qualitatively. But it can be helpful to convert the assessed gap between design and reality on each dimension into a numerical rating. For example, one could use a scale from zero to ten on which:

- 0 would indicate no discrepancy between design and reality

- 5 would indicate some degree of difference between design and reality

- 10 would indicate complete and radical difference between design and reality.

Experience from past projects suggests that adding up the rating numbers for all seven ITPOSMO dimensions offers an estimate of the likelihood of either total or partial failure, as shown in Table 2 [12]. (Of course, there is no exact calibration here; hence the value of moving to inter-subjectivity by use of group ratings and discussion.)  These ratings can be used to guide risk assessment and change management for individual projects, or used to prioritize between different projects on the basis of risk.

Table 2: Design-reality gap ratings and project risks

| Overall Rating | Likely Outcome |
| --- | --- |
| 57 - 70 | The anti-corruption initiative will almost certainly fail totally unless action is taken to close design-reality gaps. |
| 43 - 56 | The anti-corruption initiative may well fail totally unless action is taken to close design-reality gaps. |
| 29 - 42 | The anti-corruption initiative might fail totally, or might well be a partial failure unless action is taken to close design-reality gaps. |
| 15 - 28 | The anti-corruption initiative might be a partial failure unless action is taken to close design-reality gaps. |
| 0 - 14 | The anti-corruption initiative may well be successfully implemented. |

For example, a democracy initiative was proposed in West Africa with the intention of reducing fraud and making the electoral process more transparent [4]. The gap between design and ex-ante reality was analyzed using the ITPOSMO dimensions, with the result as shown in Table 3.

Table 3: Design-reality gaps analysis example: West African electoral transparency

| ITPOSMO Checklist | Inscribed Expectations in Design | Reality of Deployment Context | Design-Reality Gap Estimate |
| --- | --- | --- | --- |
| Information | Information would consist of the traditional set of constituency results, but flowing between different start and end points | Information content as per design, but with different information flow | 4.5 |
| Technology | The presence of an electronic scoreboard at national headquarters plus around 350 networked PCs, one in each constituency office | No HQ scoreboard; no PCs in constituency offices; most have faxes; a few have no phone or electricity | 7.5 |
| Processes | A new process of decentralized reporting, by which results could be declared in constituencies, then sent direct from constituencies to the central headquarters of the National Election Commission (NEC). (Voting process design no different to current reality.) | Faxing to regional NEC directors; then fax on to NEC HQ; constituencies not allowed to declare their own results. | 5 |
| Objectives and values | Elections should be determined on fair and rational grounds | Only a few overt hints of resistance to these values e.g. from staff at district level, but attitude of highest levels unclear | 5 |
| Staffing and skills | The presence of various technology installation skills prior to election, and of data entry skills and network operation and maintenance skills at election time | Only half the required number of IT staff available; no staff with data entry skills | 6 |
| Management systems and structures | The usual hierarchical management structures of the National Election Commission; regional and district offices administer election but not results | As per design except for results role of regional/district offices | 2.5 |
| Other resources | 20 million US$ to be available to cover total costs; two-year timescale for implementation | Money available; time not available | 5.5 |

The overall gap rating total for the designed project was 36, suggesting – according to Table 2 – the possibility of partial or even total failure unless action was taken. In actual fact, the initiative was a partial failure due to the inability to close gaps by making the necessary changes to reality (especially the changes to technology, skills and process redesign) within the available time, so that only small parts of the system were operational for the election.

#### The externality of anti-corruption initiative designers

Anti-corruption initiatives can be designed by many different groups, but a common pattern is for designers to be, in some way, external to the context of deployment and use. These externalities can take different forms. For example, there may be a “disciplinary externality” when the designer is drawn from a different work domain to that of the main implementers, such as a legal rather than public management background or unit. The designer will characteristically have a different educational background, a different departmental culture, even a different “language” from those who are supposed to adopt the new initiative.

As noted above, there is also the “country externality” that arises when the design is taken from a different national context to that of the users. For example, Doig et al. [8] speak of Africa being “carpet-bombed” with an anti-corruption commission model drawn from Hong Kong; a model designed within and for an entirely different set of resources and an entirely different set of “prevailing political, social and economic conditions” to the reality found in Africa.

In these situations designers will, wittingly or unwittingly, inscribe aspects of their design context into the anti-corruption initiatives. They may try to incorporate elements of local reality into the design as well. However, as Figure 1 indicates, these are assumptions, and assumptions are not necessarily an accurate reflection of reality.  In one South Asian Planning Ministry, for instance, a system was introduced to help make budgeting decisions more transparent [1]. An overseas consultant led a design team who inscribed a set of assumptions about the processes and culture of the Ministry into the system, including the assumption that decision-making about project and program budgets was formal, open and rational. In reality, decision-making in the Ministry had quite different qualities – it was informal, closed, and highly politicized – and this design-reality mismatch compromised the system being able to function effectively.

The image portrayed is that shown in Figure 2; of the “rotten coconut”. On the outside, the organization appears to adhere to “hard”, rational management norms. But there was a politicized (and corrupt) inner reality driven by quite different informal institutional values. The designers stood on the outside, from different disciplines, from outside the Ministry and led by a foreigner. Where they did engage with Ministry staff, the interaction was within the public discourse of organizational rationality, talking only about the “shell” of the coconut not the fruit inside, and thus designing a fiction that bore little relation to the true functioning of the organization.

Figure 2: The context of deployment as “rotten coconut”

#### Three design-reality gap outcomes

Using the model offered above, we could classify anti-corruption initiatives as typically falling into one of three design-reality gap outcomes. Some have a small design-reality gap right from the start. Because of the small gap, there is a small risk of failure, and a significant likelihood of successful implementation. However, because the design is not very different from the pre-existing reality, it makes little change to that reality, and so has relatively little impact on corruption. For example, some Indian government e-transparency projects have merely automated a few parts of their existing service processes (an approach Michael Hammer refers to as “paving the cowpaths” and which others, more crudely, call “putting lipstick on the face of a pig”). Those projects worked – their design was little different to previous reality – but they have made little difference to the number of citizens who must pay a bribe in order to get service [2].

The converse is a project that starts with a large gap between design and reality. One outcome is that this gap remains large, and the project therefore fails in some way. Both the West African and the South Asian examples cited above fall into this outcome category.

However, anti-corruption initiatives with large initial gaps do not always end in failure. They may find a way – during implementation – to close those gaps, and achieve success. This might mean changing the design to bring it closer to existing reality; for example by reducing the scope and ambition of the project. It will almost certainly mean changing the reality to bring it closer to the design: that is what implementation invariably involves. Or it may mean a combination of these two.

Anti-corruption reforms within Bolivia’s National Tax Service provide an example of a large design-reality gap successfully handled [35]. These reforms were ambitious, requiring changes on all of the ITPOSMO dimensions in order to combat widespread fraud. Steady changes over a number of years gradually closed the gaps by bringing reality in line with design expectations: different data was gathered on taxpayers; old and absent information technology was updated; the process for making tax payments was streamlined; more than 80% of staff were replaced and their skill sets were expanded; and so on. This steady gap closure created a new system that worked, with the level of tax evasion and the proportion of tax refunds (a key source of fraud) both significantly reduced.

#### Designing successful anti-corruption initiatives

Design of successful anti-corruption initiatives (meaning those which are successfully implemented: the extent of their success in combating corruption depends on their design objectives) requires us to pay attention to the “who” and “how” of the design process.  It is by this means that we can try ensure initiative design is more appropriate to contextual realities; a judgment that can be made during the implementation process by using the ITPOSMO gap rating approach described above.

One key will be the extent to which designers are truly exposed to the realities of the deployment context. Good practice approaches to reality diagnostics are varied. For instance, some projects use soft systems methodologies including tools such as rich pictures, which map out the true nature of processes and interests. Other projects use embedding and participation. For example, when the Sri Lankan State Accounts Department decided to introduce a more transparent approach to publication of financial statements, enabled by the Web [6], it required the long-term presence of design consultants working alongside Departmental staff. This enabled the designers to move beyond the “discourse of rationality” to a closer contextual understanding. It also enabled greater staff participation in processes of design and implementation, thus widening the foundation of inter-subjectivity on which to judge the appropriateness of that design.

The profile of designers and key users also matters. One valuable profile found on successful anti-corruption initiatives is the “hybrid” who straddles design and reality, by understanding something of both worlds: understanding both how to design and how to fit such design to actual experience from the particular reality concerned. Examples include designers previously employed by the user agency, or users with experience of consulting on and implementing anti-corruption systems in other organizations.

These actions – exposing realities, embedding, participation, use of hybrids – are all ways to help ensure that elements far-removed from local realities do not creep into anti-corruption design. They could usefully be included when drafting ToRs for anti-corruption projects. However, design-reality gaps may still be large due to the ambition of the initiative. Factors discussed above like donor politics or government timescales may prevent this being altered. But in some cases, designers have found ways to break the project down into more “bite-sized” chunks. While the ambition of the whole is not lost, within each individual component design-reality gaps are sufficiently small to make successful implementation more likely.

The Bolivian tax reform cited above did this in two ways [35]. It was incremental: taking at least five years to make the necessary changes to reality. Had it adopted a “big bang” approach that sought to make these changes rapidly, failure would have been likely. It was also modular: designing three smaller, separate initiatives – one for each part of the tax service – rather than attempting a single, one-size-fits-all design. As such we should not make the mistake of saying that implementation processes are unimportant. Rather the design and implementation processes must be seen in conjuncture.

When addressing design-reality gap closure, all the ITPOSMO dimensions are important. But six of them – ITPSMO – are largely technocratic matters. Put another way, if their design-reality gaps are sufficiently small or can be sufficiently closed, then they will enable the anti-corruption initiative to be successfully implemented. But they will not drive the initiative to succeed. For that, the real objectives and values of key stakeholders must match the design requirements; and a key – almost always implicit – design requirement is the one from political economy already identified: that powerful stakeholders must want corruption to be reduced and have the personal impetus and political will to make that happen.

The middle “O” dimension of objectives and values – which encompasses both politics and culture – is therefore the most important; explaining why so much attention has recently been paid to the acknowledgement, analysis and handling of politics and culture in anti-corruption initiatives (e.g. [5], [29]).

In this study we have taken the pulse on the fight against corruption. After two decades of trial and error the pressure is on the reformers to show results and positive impact. Our contribution is a call for a return to the basics, the level of implementation. Closing design-reality gaps will, above all, unlock the door to success. So to get the focus back on positive outcomes and sustainable interventions the status of those who design and manage interventions every day must be lifted to match the star status of those who think big on policy and overall strategy.

#### References

- Anonymous (2008). Laying Foundations for Transparency of Development Project Finances in a South Asian Ministry of Planning, eTransparency Case Study no.14, http://www.egov4dev.org accessed 13 October 2011.

- Bhatnagar, S.C. & Singh, N. (2010). Assessing the impact of e-government, Information Technologies and International Development, 6(2), 109-127.

- Blunt, P. (2002). Public Administrative Reform and Management Innovation for Developing Countries, Background paper by for the Fourth Global Forum on Reinventing Government, http://unpan1.un.org/intradoc/groups/public/documents/un/unpan006226.pdf accessed 13 October 2011.

- Boateng, K. & Heeks, R.B. (2008). Computerising Election Results Management in West Africa, eGov Project Risk Example no.2, http://www.egov4dev.org accessed 13 October 2011.

- Brinkerhoff, D.W. (2010). Unpacking the Concept of Political Will to Confront Corruption, U4 Brief no.1. Bergen, Norway: Chr. Michelsen Institute.

- Chandrasena, A.M.S.K. (2008). Web-Based Access to User-Friendly Financial Statements in Sri Lanka, eTransparency Case Study no.10, http://www.egov4dev.org accessed 13 October 2011.

- de Maria, W. (2010). The failure of the African anti-corruption effort: lessons for managers, International Journal of Management, 27(1), 117-122.

- Doig, A., Watt, D. & Williams, R. (2005). Measuring ‘Success’ in Five African Anti-Corruption Commissions, U4 Report. Bergen, Norway: Chr. Michelsen Institute.

- Fjeldstad, O.H. (2006). Corruption in tax administration: lessons from institutional reforms in Uganda. In S. Rose-Ackerman (ed.), International Handbook on the Economics of Corruption (pp. 484-511). Cheltenham: Edward Elgar.

- Grindle, M.S. (2010). Good Governance: The Inflation of an Idea, RWP10-023. Cambridge, MA: Kennedy School of Government.

- Heeks, R.B. (2005). e-Government as a carrier of context, Journal of Public Policy, 25(1), 51-74.

- Heeks, R.B. (2006). Implementing and Managing eGovernment. London: Sage.

- Heeks, R.B. (2007). Why anti-corruption initiatives fail: technology transfer and contextual collision. In S. Bracking (ed.), Corruption and Development: The Anti-Corruption Campaigns (pp. 258-272). Basingstoke, UK: Palgrave Macmillan.

- Hubbard, P. (2007). Putting the Power of Transparency in Context: Information’s Role in Reducing Corruption in Uganda’s Educations Sector, WP 136. Washington, DC: Centre for Global Development.

- Hussmann, K. & Hechler, H. (2008). Anti-Corruption Policy Making in Practice, U4 Brief no.1. Bergen, Norway: Chr. Michelsen Institute.

- IDS (2010). An Upside-down View of Governance. Brighton, UK: Institute for Development Studies.

- ITAD (2011). Joint External Anti-Corruption Evaluation, Synthesis report. Hove, UK: ITAD.

- McGee, R. & Gaventa, J. (2010). Review of Impact and Effectiveness of Transparency and Accountability Initiatives. Brighton, UK: Institute for Development Studies.

- Mutebi, A.M. (2008). Explaining the failure of Thailand’s Anti-corruption Regime, Development and Change, 39(1), 147-171.

- Persson, A., Rothstein, B. & Teorell, J. (2010). The Failure of Anti-Corruption Policies: A Theoretical Mischaracterization of the Problem, Working Paper 19. Gothenburg, Sweden: Quality of Government Institute, University of Gothenburg.

- Pritchett, L. (2002). It pays to be ignorant: a simple political economy of rigorous program evaluation, Policy Reform, 5(4), 251-269.

- Pritchett, L., Woolcock, M. & Andrews, M. (2010). Capability Traps? The Mechanisms of Persistent Implementation Failure, Working Paper 234. Washington, DC: Center for Global Development.

- Reinikka, R. & Svensson, J. (2005). Fighting corruption to improve schooling, Journal of the European Economic Association, 3(2-3), 1-9.

- Rose-Ackerman, S. (1999). Corruption and Government: Causes, Consequences, and Reform. Cambridge, UK: Cambridge University Press.

- Scanteam (2009). Anti-Corruption Approaches: A Literature Review. Oslo: Norad.

- Sundet, G. (2008). Following the Money: Do Public Expenditure Tracking Surveys Matter, Issue Paper 2008:09. Bergen, Norway: Chr. Michelsen Institute.

- Tisne, M. & Smilov, D. (2004). From the Ground Up: Assessing the Record of Anti-corruption Assistance in Southeastern Europe, Policy Studies Series 2004. Budapest: Center for Policy Studies, Central European University.

- Trivunovic, M. (2011). Countering NGO Corruption: Rethinking the Conventional Approaches, U4 Issue Paper 2011:3. Bergen, Norway: Chr. Michelsen Institute.

- Unsworth, S. (2007). Rethinking Governance to Fight Corruption, U4 Brief no.7. Bergen, Norway: Chr. Michelsen Institute.

- Vian, T., Savedoff, W.D. & Mathisen, H. (2010). Anticorruption in the Health Sector. Herndon, VA: Kumarian Press.

- Williams, R. & Doig, A. (2007). Achieving Success and Avoiding Failure in Anti-Corruption Commissions, U4 Brief no.1. Bergen, Norway: Chr. Michelsen Institute.

- World Bank (2007). Strengthening World Bank Group Engagement on Governance and Anticorruption. Washington, DC: World Bank.

- World Bank (2010). First “International Corruption Hunters Alliance” Meets at World Bank to Accelerate Global Enforcement Action, Press Release no. 2011/216/INT. Washington, DC: World Bank.

- World Bank/Independent Evaluation Group (2008). Public Sector Reform: What Works and Why?, Washington, DC: World Bank.

- Zuleta, J.C. (2008). Combating Corruption in the Revenue Service, U4 Brief no.14. Bergen, Norway: Chr. Michelsen Institute.

# Footnotes

The U4 Anti-Corruption Resource Centre assists donor practitioners in more effectively addressing corruption challenges through development support utilizing extensive online resources, a helpdesk and online as well as in-country training on anti-corruption measures. The University of Manchester's Centre for Development Informatics has worked with government and other agencies on, among other things, the use of informatics to address issues of corruption, transparency and accountability.

On transparency and accountability initiatives alone thousands of projects are in operation [18].

Anti-corruption measures are seldom amendable to impact evaluation with randomized control groups.

Capitation grants reaching schools went up from 22% to 80% as a result from a nationwide transparency and local engagement program.

http://info.worldbank.org/governance/wgi/index.asp

But we still lack solid knowledge and understanding on how to mainstream anti-corruption into sector interventions.

For a well argued critique of principal agent theory as the dominant paradigm on anti-corruption, see

[20].

This is dubbed “isomorphic mimicry” by Pritchett et al. [22]: the ability of an organisation to sustain legitimacy through imitation of the forms of modern institutions without their functionality.

# Text boxes

Assumptions

Insertion

Inscription

Reality of

Deployment Context

Anti-Corruption Initiative Design

Design Context

Design-Reality Gap

Rational Image/Shell

Inner Politicised Reality